## Model Pathway
|  |  | IDEATION |  |  |  | INTEGRATION |  |  |  | IMPLEMENTATION |  |  | INNOVATION
|  | Gate | Business Case | GATE 1A | GATE 1B | GATE 1C Concept Design 1C | GATE 2 | GATE 3A | GATE 3B | GATE 4 | GATE 5 | GATE 6 | GATE 7 | GATE 8
| OWNER | Objective | Project Feasability | Strategic Vision | Strategic Definition | Concept Design | Pre-TP Lodgement | 60% DD (Optional At Risk - DD) | Post Town Planning | Pre-Tender | Post-Tender | Pre- Construction | Construction | Operation
| Program Scheduler | Development Program | Prepare Development Program | Review and Update Development Program | Review and Update Development Program | Review and Update Development Program | Review and Update Development Program | Review and Update Development Program | Review and Update Development Program | Review and Update Development Program | Review and Update Development Program | Review and Update Development Program | Review and Update Development Program | Review and Update Development Program
GATE APPROVAL DELIVERABLES | Design Vision Team | Principal's Project Requirements | Statement of Project Aims | Development Brief Approach to Visioning | Development Brief Visioning Document | PPR Overview Draft | PPR Overview PPR Specification/Schedule | PPR Overview - Update | PPR Overview - Update | PPR Overview - Update | PPR Overview - Update | PPR Overview - Update | PPR and Approved Design Compliance Monitoring | PPR Review
| Risk and Commercial Team | Yield / Functional Objectives | Site Yield Analysis | From Business Case | Functional Area Schedule | Area Schedule | Comprehensive Area Schedule | Comprehensive Area Schedule Preliminary Room Data Sheets | Comprehensive Area Schedule Room Data Sheets with ID | Reconfirmation of Development Functional Areas and Units | Reconfirmation of Development Functional Areas and Units | Reconfirmation of Development Functional Areas and Units | Monitoring of Development Functional Areas and Units
| Risk and Commercial Team | Risk Management & Enabling Works | Draft Risk Register | Draft Risk Register | Site and Authorities Risk Matrix - Desktop | Site and Authorities Risk Matrix - Mitigation and Costs Strategy | Site, Authority and Headworks Matrix Enabling Works Strategy & Budget | Site, Authority and Headworks Matrix Enabling Works Update | Site, Authority and Headworks Matrix Enabling Works Update | Site, Authority and Headworks Matrix Enabling Works Close-Out Risk-Transfer under D&C | Site, Authority and Headworks Matrix Key Delivery Risks and Mitigation Strategy | Site, Authority and Headworks Matrix Delivery Risk and Mitigation Status | Site, Authority and Headworks Matrix Delivery Risk and Mitigation Status | Residual Risks and Mitigation Strategy
| Risk and Commercial Team | Feasibility & Funding | Feasibilty Study & NPV Analysis Sale rate inputs to Cost Plan / Feasibility | Target Yield including amenity ratios & scenarios | Feasibility Update inputs and review objectives Stock requirements analysis | Feasibility Update inputs and review objectives | Feasibility Update inputs and review objectives | Feasibility Update inputs and review objectives | Feasibility Update inputs and review objectives | Feasibility Update inputs and review objectives | Feasibility Update; Key Funding Matters | Feasibility Update; Commercial Close | Feasibilty Update | Report on final CAPEX and OPEX forecasts
| Risk and Commercial Team | Cost Plan | Cost Plan A Efficiency Analysis | From Business Case | Cost Plan B Report | Cost Plan B-C Report | Cost Plan C Report | Cost Plan C Update VM Initiatives Costed For Consideration | Cost Plan C Update Impacts of Town Planning | Cost Plan D / Rated BoQ | Tender Analysis VM Validation | Cash Flow Forecast | Cash Flow Monitoring Commercial and Financial Monitoring and Reporting | Data Capture and Report
| Risk and Commercial Team | Budget | Draft Development Cashflow. Formal approval for Gate 1 > 2 Budget and Resources | From Business Case | Budget Update including forecast individual design, marketing, headworks and authority costs. | Gate 1B Firm Budget developed with a cashflow with traffic light indication of budgets still at large. | Report on any budget and cashflow adjustments. | Report on any budget and cashflow adjustments. | Report on any budget and cashflow adjustments. | Report on any budget and cashflow adjustments. | Report on any budget and cashflow adjustments. | Report on any budget and cashflow adjustments. | PCG Monitoring and Reporting
| Comms and Engagement Team | Marketing / Communications |  | Competitor & Market Summary; High-level Strategy | Preliminary Marketing Strategy; Risks and Opportunities | Marketing Strategy Community Engagement Activities | Marketing Strategy - Update with Key Activities and Budget | Marketing Strategy - Update with Key Activities and Budget | Marketing Strategy - Update with Key Activities and Budget | Marketing Strategy - Update with Key Activities and Budget. | Marketing Strategy - Update with Key Activities and Budget. | Marketing Strategy - Update with Key Activities and Budget. | Marketing Strategy - Update with Key Activities and Budget. | Launch
| Delivery Team | Design Deliverables |  | Preliminary Benchmarking Document | Benchmarking Document [Pin-up] | Conceptual Design Touch and Feel [Pin-up] | Developed Design (all disciplines) 25% Renders & Exterior Finishes [Pin-up] | Developed Design 60% (all disciplines) Interior Design [Pin-up] | Developed Design - Town Planning Implications | Complete Contract Design - All Disciplines [Pin-up] | Cut-sheets outlining propsed VM Recommendations [Pin-up] | Completed Design incoporating all VM and for Construction |  | As-Built Documentation and Compliance
| Delivery Team | Reports | Site Condition Reports, Town Planning Opinion |  | Design Reports: ESD, Structure, Services, ID, Landscape | Design Reports - All Disciplines | Design Reports - All Disciplines with additional Statutory/Regulatory Inputs | Anticipated TP Condition Discharge Strategy | TP Condition Discharge Strategy Signage and Wayfinding | TP Condition Discharge Matrix | TP Condition Discharge Matrix Update VM Adoption Strategy | TP Condition Discharge Matrix Update | TP Condition Discharge Matrix Update | O&M Manuals Defecting and Commissioning
| Delivery Team | FM |  | Asset Management Strategy and Design Objectives | Asset Management Brief | Asset Lifecycle Plan and Inputs & Operator Assumptions; Internal FM endorsement | Asset Management – Maintenance Cost Plan and Technology Report; Internal FM endorsement | Asset Management Report – Design Compliance Report inc VM | Asset Management Report – Design Compliance Report Update | Asset Management – Design Compliance Report Update; Internal FM endorsement | FM Post Tender Report - Implications of proposed VM initiatives | Maintenance Cost Plan Update | Asset Management – Inspection and Test Plans Asset Data for CMMS input | Inductions and operational strategy; Internal FM endorsement
| Delivery Team | Procurement |  | Consultant RFP | Consultants Appointed | Preliminary Procuremnet Strategy and Construction Market Forecast | Construction Market Forecast & Procurement Strategy | Construction Market Forecast | Procurment Strategy: Construction Market Update; and Contractor Shortlist to EOI Process | Procurement Strategy: Construction Market Update; outcome of EOI Prequalification; Tender List; and Key Commercial Terms for D&C | Present Preferred Contractor Profile Price, Personnel & Programme Methodology Key Commercial Terms | Fast-track Prototype Room/s Prototypes and Samples PCG Approach and Reporting FF&E Procurement Strategy | Prototypes and samples FFE Procurement
| Operational Activation Team |  |  |  |  | identify relevant internal stakeholders for input into design process. | INTEGRATION GATE 3B: Site Activation Plan; INNOVATION GATE 8: Procure Equipment Training and Induction Bump In | Commence Operations
|  | Executive Approval | HOLD POINT - TRUST Trust approval of business case, development budget | 1. COO conceptual approval for approach (plant , EN providers etc) | 1. Develop proposed Conceptual Design | HOLD POINT - TRUST 1. Prepare Town Planning 2. Adopt Marketing Strategy | 1. Lodge for Town Planning 2. Continue at-risk Design Development 3. Adopt Enabling Works Strategy | 1. Adoopt recommended VMs 2. Continue at-risk Design Development | 1. Document for Tender 2. Procurement Strategy | HOLD POINT - TRUST 1. Design for Tender 2. Tender Process | 1. Proceed to Contract | 1. Commence Construction
|  | SMCT Internal Stakeholder Inputs | PMO Sales | PMO Sales Marketing and Comms Facilties | Finance IT PMO Facilites Sales Hospitality Marketing and Comms Corporate Governance Operations | PMO Facilites Sales Hospitality Marketing and Comms Operations | Finance IT PMO Facilites Sales Hospitality Marketing and Comms Corporate Governance Operations | Finance IT PMO Facilites Sales Hospitality Marketing and Comms Corporate Governance Operations | Finance IT PMO Facilites Sales Hospitality Marketing and Comms Corporate Governance Operations | Finance IT PMO Facilites Sales Hospitality Marketing and Comms Corporate Governance Operations | Finance IT PMO Facilites Sales Hospitality Marketing and Comms Corporate Governance Operations | Finance IT PMO Facilites Sales Hospitality Marketing and Comms Corporate Governance Operations | Finance IT PMO Facilites Sales Hospitality Marketing and Comms Corporate Governance Operations | Finance IT PMO Facilites Sales Hospitality Marketing and Comms Corporate Governance Operations
|  | Objectives | Establish initial project feasabilty and direction | Prior to commencing any design, reassess and challenge all existing assumptions methodically. Establish a developoment brief that sets measurable targets for all functional, technical, cost and revenue assumptions. Co-author a benchmarking document to calibrate participants' shared vision and remove bias. | Interrogate the targets and objectives set in the development brief using data and research. Conduct high-level yield studies against market insights to assess revenue and cost assumptions. Develop benchmark document to better represent outcomes of research and to inform the cost plan. | Using the tested and agreed design parameters, begin schematic design testing to validate yield and product objectives. Risks, including economic, planning, authority and headworks considerations are evaluated to inform design direction. Schematic design for key disciplines are prepared to inform scope and objectives for the feasibility and cost plan. | Prior to lodgement the development must be optimised against all objectives as beyond this point change will likely result in abortive design and program slippage. All conceivable risks have been identified, mitigated or managed. Enabling works strategies are implemented to reduce site and authority risk to time and later contractor procurement. | Developed design representing full scope and performance expectations evaluated against objectives. Opportunity respond to market and anticipated planning outcomes prior to balance of design coordination. Contractor procurement strategy reviewed to inform residual documentation approach. | Opportunity to reflect on outcomes of planning process and current state of economy, marketing, sales and other coroporate objectives. Take stock of town planning impacts and determine if it materially impacts the development objectives and consider time and cost implications of progressing or revisiting strategy. | Contract documentation with full scope and performance expectations resolved against the PPR. Any residual development risks transferred to the contractor where cost-effective and conventional. A comprehensive cost plan or rated BoQ process involving detailed briefing and review by all disciplines ensures the PPR scope is resolved and the market pricing is highly competitive and without fatigue. | Prior to contract and commencement the design is updated to realise all targeted VM or SMCT-lead changes prior to commencement. Residual risk transfer and responsibilities are matrixed and understood by all parties. | Direction to proceed to Building Permit and Commencement of Construction. Commitments to prototypes, samples and direct procurement are planned and understood.

## HR Status
|  |  | IDEATION |  |  |  | INTEGRATION |  |  |  | IMPLEMENTATION |  |  | OPERATION | PROJECT REVIEW
|  | Gate | Business Case | GATE 1A | GATE 1B | GATE 1C Concept Design 1C | GATE 2 | GATE 3A | GATE 3B | GATE 4 | GATE 5 | GATE 6 | GATE 7 | GATE 8 | GATE 9
| OWNER | Objective | Project Feasability | Strategic Vision | Strategic Definition | Concept Design | Pre-TP Lodgement | 60% DD (Optional At Risk - DD) | Post Town Planning | Pre-Tender | Post-Tender | Pre- Construction | Construction | Operation | Continuous Improvement
| Program Scheduler | Development Program | Prepare Development Program | Review and Update Development Program | Review and Update Development Program | Review and Update Development Program | Review and Update Development Program | Review and Update Development Program | Review and Update Development Program | Review and Update Development Program | Review and Update Development Program | Review and Update Development Program | Review and Update Development Program | Review and Update Development Program
GATE APPROVAL DELIVERABLES | Design Vision Team | Principal's Project Requirements | Statement of Project Aims | Development Brief Approach to Visioning | Development Brief Visioning Document | PPR Overview Draft | PPR Overview PPR Specification/Schedule | PPR Overview - Update | PPR Overview - Update | PPR Overview - Update | PPR Overview - Update | PPR Overview - Update | PPR and Approved Design Compliance Monitoring | PPR Review | Review success against original objectives and conduct lessons learnt review.
Status as at end July 2020
| Risk and Commercial Team | Yield / Functional Objectives | Site Yield Analysis | From Business Case | Functional Area Schedule | Area Schedule | Comprehensive Area Schedule | Comprehensive Area Schedule Preliminary Room Data Sheets | Comprehensive Area Schedule Room Data Sheets with ID | Reconfirmation of Development Functional Areas and Units | Reconfirmation of Development Functional Areas and Units | Reconfirmation of Development Functional Areas and Units | Monitoring of Development Functional Areas and Units |  | Review success against original objectives and conduct lessons learnt review.
Status as at end July 2020
| Risk and Commercial Team | Risk Management & Enabling Works | Draft Risk Register | Draft Risk Register | Site and Authorities Risk Matrix - Desktop | Site and Authorities Risk Matrix - Mitigation and Costs Strategy | Site, Authority and Headworks Matrix Enabling Works Strategy & Budget | Site, Authority and Headworks Matrix Enabling Works Update | Site, Authority and Headworks Matrix Enabling Works Update | Site, Authority and Headworks Matrix Enabling Works Close-Out Risk-Transfer under D&C | Site, Authority and Headworks Matrix Key Delivery Risks and Mitigation Strategy | Site, Authority and Headworks Matrix Delivery Risk and Mitigation Status | Site, Authority and Headworks Matrix Delivery Risk and Mitigation Status | Residual Risks and Mitigation Strategy | Review of final risks and opportunities, and success in mitigation/realisation.
Status as at end July 2020
| Risk and Commercial Team | Feasibility & Funding | Feasibilty Study & NPV Analysis Sale rate inputs to Cost Plan / Feasibility | Target Yield including amenity ratios & scenarios | Feasibility Update inputs and review objectives Stock requirements analysis | Feasibility Update inputs and review objectives | Feasibility Update inputs and review objectives | Feasibility Update inputs and review objectives | Feasibility Update inputs and review objectives | Feasibility Update inputs and review objectives | Feasibility Update; Key Funding Matters | Feasibility Update; Commercial Close | Feasibilty Update | Report on final CAPEX and OPEX forecasts | Lessons learnt review against final CAPEX/OPEX outcomes
Status as at end July 2020
| Risk and Commercial Team | Cost Plan | Cost Plan A Efficiency Analysis | From Business Case | Cost Plan B Report | Cost Plan B-C Report | Cost Plan C Report | Cost Plan C Update VM Initiatives Costed For Consideration | Cost Plan C Update Impacts of Town Planning | Cost Plan D / Rated BoQ | Tender Analysis VM Validation | Cash Flow Forecast | Cash Flow Monitoring Commercial and Financial Monitoring and Reporting | Data Capture and Report | Review of contractor and consultant performance and lessons learnt
Status as at end July 2020
| Risk and Commercial Team | Budget | Draft Development Cashflow. Formal approval for Gate 1 > 2 Budget and Resources | From Business Case | Budget Update including forecast individual design, marketing, headworks and authority costs. | Gate 1B Firm Budget developed with a cashflow with traffic light indication of budgets still at large. | Report on any budget and cashflow adjustments. | Report on any budget and cashflow adjustments. | Report on any budget and cashflow adjustments. | Report on any budget and cashflow adjustments. | Report on any budget and cashflow adjustments. | Report on any budget and cashflow adjustments. | PCG Monitoring and Reporting |  | Review expenditure performance and lessons learnt review
Status as at end July 2020
| Comms and Engagement Team | Marketing / Communications |  | Competitor & Market Summary; High-level Strategy | Preliminary Marketing Strategy; Risks and Opportunities | Marketing Strategy Community Engagement Activities | Marketing Strategy - Update with Key Activities and Budget | Marketing Strategy - Update with Key Activities and Budget | Marketing Strategy - Update with Key Activities and Budget | Marketing Strategy - Update with Key Activities and Budget. | Marketing Strategy - Update with Key Activities and Budget. | Marketing Strategy - Update with Key Activities and Budget. | Marketing Strategy - Update with Key Activities and Budget. | Launch | Review of success of strategy and lessons learnt review
Status as at end July 2020
| Delivery Team | Design Deliverables |  | Preliminary Benchmarking Document | Benchmarking Document [Pin-up] | Conceptual Design Touch and Feel [Pin-up] | Developed Design (all disciplines) 25% Renders & Exterior Finishes [Pin-up] | Developed Design 60% (all disciplines) Interior Design [Pin-up] | Developed Design - Town Planning Implications | Complete Contract Design - All Disciplines [Pin-up] | Cut-sheets outlining propsed VM Recommendations [Pin-up] | Completed Design incoporating all VM and for Construction |  | As-Built Documentation and Compliance | Review of performance against stated deliverables. Lessons learnt review
Status as at end July 2020
| Delivery Team | Reports | Site Condition Reports, Town Planning Opinion |  | Design Reports: ESD, Structure, Services, ID, Landscape | Design Reports - All Disciplines | Design Reports - All Disciplines with additional Statutory/Regulatory Inputs | Anticipated TP Condition Discharge Strategy | TP Condition Discharge Strategy Signage and Wayfinding | TP Condition Discharge Matrix | TP Condition Discharge Matrix Update VM Adoption Strategy | TP Condition Discharge Matrix Update | TP Condition Discharge Matrix Update | O&M Manuals Defecting and Commissioning | Lessons learnt review
Status as at end July 2020
| Delivery Team | FM |  | Asset Management Strategy and Design Objectives | Asset Management Brief | Asset Lifecycle Plan and Inputs & Operator Assumptions; Internal FM endorsement | Asset Management – Maintenance Cost Plan and Technology Report; Internal FM endorsement | Asset Management Report – Design Compliance Report inc VM | Asset Management Report – Design Compliance Report Update | Asset Management – Design Compliance Report Update; Internal FM endorsement | FM Post Tender Report - Implications of proposed VM initiatives | Maintenance Cost Plan Update | Asset Management – Inspection and Test Plans Asset Data for CMMS input | Inductions and operational strategy; Internal FM endorsement | Review against original FM/Asset aims, and lessons learnt review
Status as at end July 2020
| Delivery Team | Procurement |  | Consultant RFP | Consultants Appointed | Preliminary Procuremnet Strategy and Construction Market Forecast | Construction Market Forecast & Procurement Strategy Engage design architects. | Construction Market Forecast | Procurment Strategy: Construction Market Update; and Contractor Shortlist to EOI Process | Procurement Strategy: Construction Market Update; outcome of EOI Prequalification; Tender List; and Key Commercial Terms for D&C | Present Preferred Contractor Profile Price, Personnel & Programme Methodology Key Commercial Terms | Fast-track Prototype Room/s Prototypes and Samples PCG Approach and Reporting FF&E Procurement Strategy | Prototypes and samples FFE Procurement
Status as at end July 2020
| Operational Activation Team |  |  |  | Stakeholder input into design requirements. Business Transformation input into design requirements. |  | GATE 3A: Site Activation Plan; GATE 7: Procure Equipment Training and Induction Bump In; GATE 8: Commence Operations; GATE 9: Review status of operation and opportunities for efficiency and improvement. Review success and identify areas for improvement.
|  | Executive Approval | HOLD POINT - TRUST Trust approval of business case, development budget | 1. COO conceptual approval for approach (plant , EN providers etc) | 1. Develop proposed Conceptual Design (change language to masterplan) | HOLD POINT - TRUST 1. Prepare Town Planning 2. Adopt Marketing Strategy | 1. Lodge for Town Planning 2. Continue at-risk Design Development 3. Adopt Enabling Works Strategy | 1. Adoopt recommended VMs 2. Continue at-risk Design Development | 1. Document for Tender 2. Procurement Strategy | HOLD POINT - TRUST 1. Design for Tender 2. Tender Process | 1. Proceed to Contract | 1. Commence Construction |  |  | Review against original objectives, lessons learnt
Status as at end July 2020
|  | Internal Stakeholder Inputs | PMO Sales | PMO Sales Marketing and Comms Facilties | Finance IT PMO Facilites Sales Hospitality Marketing and Comms Corporate Governance Operations | PMO Facilites Sales Hospitality Marketing and Comms Operations | Finance IT PMO Facilites Sales Hospitality Marketing and Comms Corporate Governance Operations | Finance IT PMO Facilites Sales Hospitality Marketing and Comms Corporate Governance Operations | Finance IT PMO Facilites Sales Hospitality Marketing and Comms Corporate Governance Operations | Finance IT PMO Facilites Sales Hospitality Marketing and Comms Corporate Governance Operations | Finance IT PMO Facilites Sales Hospitality Marketing and Comms Corporate Governance Operations | Finance IT PMO Facilites Sales Hospitality Marketing and Comms Corporate Governance Operations | Finance IT PMO Facilites Sales Hospitality Marketing and Comms Corporate Governance Operations | Finance IT PMO Facilites Sales Hospitality Marketing and Comms Corporate Governance Operations
|  | Objectives | Establish initial project feasabilty and direction | Prior to commencing any design, reassess and challenge all existing assumptions methodically. Establish a developoment brief that sets measurable targets for all functional, technical, cost and revenue assumptions. Co-author a benchmarking document to calibrate participants' shared vision and remove bias. | Interrogate the targets and objectives set in the development brief using data and research. Conduct high-level yield studies against market insights to assess revenue and cost assumptions. Develop benchmark document to better represent outcomes of research and to inform the cost plan. | Using the tested and agreed design parameters, begin schematic design testing to validate yield and product objectives. Risks, including economic, planning, authority and headworks considerations are evaluated to inform design direction. Schematic design for key disciplines are prepared to inform scope and objectives for the feasibility and cost plan. | Prior to lodgement the development must be optimised against all objectives as beyond this point change will likely result in abortive design and program slippage. All conceivable risks have been identified, mitigated or managed. Enabling works strategies are implemented to reduce site and authority risk to time and later contractor procurement. | Developed design representing full scope and performance expectations evaluated against objectives. Opportunity respond to market and anticipated planning outcomes prior to balance of design coordination. Contractor procurement strategy reviewed to inform residual documentation approach. | Opportunity to reflect on outcomes of planning process and current state of economy, marketing, sales and other coroporate objectives. Take stock of town planning impacts and determine if it materially impacts the development objectives and consider time and cost implications of progressing or revisiting strategy. | Contract documentation with full scope and performance expectations resolved against the PPR. Any residual development risks transferred to the contractor where cost-effective and conventional. A comprehensive cost plan or rated BoQ process involving detailed briefing and review by all disciplines ensures the PPR scope is resolved and the market pricing is highly competitive and without fatigue. | Prior to contract and commencement the design is updated to realise all targeted VM or SMCT-lead changes prior to commencement. Residual risk transfer and responsibilities are matrixed and understood by all parties. | Direction to proceed to Building Permit and Commencement of Construction. Commitments to prototypes, samples and direct procurement are planned and understood.

## Gates
Parent Project | Box Hill Aged Care Development
Child Projects | Acquisition
Gate 1a - Strategic Vision
Gate 1b - Strategic Definition
Gate 1c - Concept Design
Gate 2 - Pre- Town Planning Lodgement
Gate 3a - 60% DD
Gate 3b - Post Town Planning Review
Gate 4 - Pre-Tender
Gate 5 - Post Tender
Gate 6 - Pre-construction
Gate 7 - Operation

## Program
|  | 2020 | [7 empty] | 2021 | [11 empty] | 2022 |  | 2023
|  | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | June | July
ESTABLISH DEVELOPMENT | Feasibility
Due Dilligence and Acquisition
Strategic Vision
Strategic Definition
Concept Design
TOWNPLANNING & MARKETING | Town Planning Documentation
Town Planning Approval
Marketing Package
Marketing Launch
Opening
DEVELOPMENT & DOCUMENTATION | Design Development to 60%
Design Development to Tender
PROCURE AND DELIVER | Enabling Works
Prequalification EOI
Tender
Negotiate > Award
Commence
Completion
Operation
|  | GATE 1A | GATE 1B | GATE 1C |  |  | GATE 2 |  | GATE 3A |  | GATE 3B |  |  | GATE 4 |  |  |  | GATE 5 |  |  | GATE 6 |  |  | GATE 7