## PM
Project | Phillip Island Nature Parks PMF
Total Fee Estimate | 36529.2 |  |  |  | Overhead Contribution |  | 4562.88
Forecast Margin | 11981.92
Margin % | 32.8%
Overhead and Margin
Overhead | 24% | Proposal Date |  | 2024-12-05
Margin | 50% | Expected Commencement |  | 2025-01-06 | Escalation Rate |  | 5%
Disbursement Mark Up | 20% | Expected Completion |  | 2025-04-30 | Escalation This Fee |  | 0%
Role | Director | Project Director | Senior Development Manager | Project Manager | Superintendent | Development Manager
Base Rate | 194 | 143 | 130 | 78 | 190 | 78
Cost Rate | 240.56 | 177.32 | 161.2 | 96.72 | 235.6 | 96.72
Charge Rate | 360.84 | 265.98 | 241.8 | 145.08 | 353.4 | 145.08
Tasks | Hours | Hours | Hours | Hours | Hours | Hours | Charge | Cost
Phase 1 - Part 1 - Discovery | [6 empty] | 0 | 0
Issue RFI | 2 | [5 empty] | 721.68 | 481.12
Review Existing Documents, Regulatory Requirements | 16 | [5 empty] | 5773.44 | 3848.96
Wokshop | 8 | [5 empty] | 2886.72 | 1924.48
Phase 1 - Part 2 - Design | [6 empty] | 0 | 0
Develop PMF | 16 | [5 empty] | 5773.44 | 3848.96
Framework Review Workshop | 8 | [5 empty] | 2886.72 | 1924.48
Complete Draft Framework | 4 | [5 empty] | 1443.36 | 962.24
Phase 2 - Policies and Procedures | [6 empty] | 0 | 0
Develop Policies and Procedures | 16 | [5 empty] | 5773.44 | 3848.96
Polciy and Procedure Workshop | 8 | [5 empty] | 2886.72 | 1924.48
Complete Draft Procedures | 4 | [5 empty] | 1443.36 | 962.24
Phase 3 - Consultation | [6 empty] | 0 | 0
Consultation Briefing | 8 | [5 empty] | 2886.72 | 1924.48
Consultation Report | 4 | [5 empty] | 1443.36 | 962.24
Phase 4 - Final Framework | [6 empty] | 0 | 0
Complete and Issue | 4 | [5 empty] | 1443.36 | 962.24
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
Total Hours | 98 | 0 | 0 | 0 | 0 | 0
Disbursement |  |  | Qty | Unit | Rate | Cost | Charge
Travel |  |  | 1144 | KMs | 0.85 | 972.4 | 1166.88 | 972.4
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[7 empty] | 36529.2 | 24547.28