## Pathway
PLAN OF WORK PATHWAY GATES - CAPEX |  |  | PHASE
|  |  | DEFINITION | DESIGN |  | DELIVERY
Gates | Gate |  | GATE 1 | GATE 2 | GATE 3 | GATE 4 | GATE 5
|  |  | Project Establishment | Design | Tender | Construction | Operation
| Objectives |  | Establish project budget, schedule and scope deliverables, and establish governance framework | Complete design tasks in preparation for tender | Tender works, and seek approval to proceed to delivery | Deliver the works in accordance with the agreed scope, schedule and budget | Transition to operational state and hand over to operational owner
Timing | Commencement: |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31
| Target Gate Approval Date: |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31
Approvals | Expenditure Approvals |  | Project Budget |  | Delivery Contract
| Approver (to move to next Gate) |  | General Manager - Assets | General Manager - Assets | General Manager - Assets or Chief Property Officer | General Manager - Assets | General Manager - Assets
| Documents for Gate Approval |  | Plan of Work | Design or Scope | Delivery Contract | Defect Register | Project Close Out Meeting Minutes
|  |  | Budget | Budget Update | Budget Update | Final Budget
|  |  | Schedule | Schedule | Schedule | Project Handover Checklist
|  |  | Risk Register | Risk Register | Risk Register
| Gateway Approval Stakeholder Referrals |  | Operational Owner | Operational Owner | Operational Owner | Operational Owner | Operational Owner
| Function | Owner | Tasks
GATE TASKS and DELIVERABLES | 1. Project Scope | Project Lead | Project Scope clearly defined for consultant briefing | Scope of works defined in tender documents | Project scope captured in delivery contract |  | Review in project close out
| 2. Design Deliverables | Project Lead |  | Design complete for tender | For construction drawings issued |  | As built and record documentation
| 3. Safety in Design | Project Lead |  | Safety in design review |  |  | Review in project close out
| 4. Risk Management | Project Lead | Project risk register established | Risk register update | Risk register update | Risk register update | Review in project close out
| 6. Operational Impact | Operational Owner |  | Completion requirements checklist Facility operational requirements |  |  | Handover to operations including training, operational documents, etc. Asset management system data.
| 7. Procurement | Project Lead | Procurement Strategy including form of contract | Tender documents | Contractor reccomendation Delivery contract |  | Review in project close out
| 8. Budget | Project Lead | Detailed project budget establshed | Budget Update | Budget Update | Budget Update | Final budget close out
| 9. Schedule | Project Lead | Project schedule established | Schedule update | Schedule update |  | Review in project close out
| 10. Communications and Engagement | Operational Owner | Stakeholder engagement requirements defined | Stakeholder requirements communicated to Project Owner |  | Stakeholder engagement as required | Review in project close out
Note on H3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These are not separate gates (3a, 3b) as there is no additional approval requirements

## Gates
Kew Development
Acquisition
Gate 1a - Strategic Vision
Gate 1b - Strategic Definition
Gate 1c - Concept Design
Gate 2 - Pre- Town Planning Lodgement
Gate 3a - 60% DD
Gate 3b - Post Town Planning Review
Gate 4 - Pre-Tender
Gate 5 - Post Tender
Gate 6 - Pre-construction
Gate 7 - Operation

## Program
|  | 2020 | [7 empty] | 2021 | [11 empty] | 2022 |  | 2023
|  | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | June | July
ESTABLISH DEVELOPMENT | Feasibility
| Due Dilligence and Acquisition |  |  | Review with key milestones from this policy
Strategic Vision
Strategic Definition
Concept Design
TOWNPLANNING & MARKETING | Town Planning Documentation
Town Planning Approval
Marketing Package
Marketing Launch
Opening
DEVELOPMENT & DOCUMENTATION | Design Development to 60%
Design Development to Tender
PROCURE AND DELIVER | Enabling Works
Prequalification EOI
Tender
Negotiate > Award
Commence
Completion
Operation
|  | GATE 1A | GATE 1B | GATE 1C |  |  | GATE 2 |  | GATE 3A |  | GATE 3B |  |  | GATE 4 |  |  |  | GATE 5 |  |  | GATE 6 |  |  | GATE 7